## Untitled spreadsheet - Sheet1
Clear Wall: Client (MagnetRock) vs Developer (Mapsi Integration Team)
Phase 1: Pre-Project Setup
Step | MagnetRock PetCare (Client) | Mapsi Integration Team (You) | Deliverable | Timeline
Contract | Sign contract, pay 50% deposit (£9,000) | Send contract, invoice | Signed contract, payment received | Day -2
Kickoff Call | Attend 30-min call, answer questions | Run call, confirm requirements, set expectations | Aligned on scope, timeline | Day -2
Access - Vercel | Go to vercel.com → Settings → Members → Invite developer's email | Accept invitation | Developer has Vercel access | Day -1
Access - GitHub | Go to github.com/magnetrock/repo → Settings → Collaborators → Add developer | Accept invitation | Developer has GitHub access | Day -1
Clinic Data | Review extracted list, send corrections (phone numbers, hours, closed clinic) | Extract clinic data from website, send for verification | Verified clinics.json file | Day -1
Coverage Zones | Decide: Postcodes (Central=EC,WC) or Drive-time (15-min radius) | Explain options, recommend approach | Coverage strategy agreed | Day 0
Mapsi Account Approval | Approve £9/month subscription for Mapsi API | Sign up for Mapsi, generate API key | API key active | Day 0
Phase 2: Week 1 - Core Features
Step | MagnetRock PetCare (Client) | Mapsi Integration Team (You) | Deliverable | Timeline
Foundation | None - no action needed | Create feature branch, build static pages, deploy preview | Preview URL with homepage/services/about | Day 1
Map Display | None - no action needed | Add Leaflet map, Mapsi tiles, 12 clinic markers | Interactive map on /locations page | Day 2
Review Day 2 | Test preview URL, report if clinic info is wrong | Send preview link, wait for feedback | Feedback collected | Day 2
Search Feature | None - no action needed | Add search bar, Mapsi Geocoding API, "Use My Location" button | Search by postcode working | Day 3
Nearest Clinics | None - no action needed | Calculate distances (Haversine), display top 3 | Nearest clinics ranked | Day 3
Routing | None - no action needed | Add Mapsi Routing API, draw routes on map, turn-by-turn | "Get Directions" working | Day 4
Week 1 Review | Watch 3-min demo video, test on mobile, provide feedback by Monday | Record demo video, create review doc, send to client | Feedback deadline set | Day 5
Weekend Testing | Test preview on personal phone, try searching home address, gather team feedback | Fix bugs from testing, cross-browser QA | No action - weekend | Day 6-7
Feedback Response | Send consolidated feedback (typos, errors, change requests) | None - waiting for client | Email with feedback items | Day 7 (Mon AM)
Phase 3: Week 2 - Advanced Features
Step | MagnetRock PetCare (Client) | Mapsi Integration Team (You) | Deliverable | Timeline
GeoJSON Zones | None - no action needed | Research postcodes, create 3 zone polygons (Central/Inner/Outer), add to map | Visual coverage zones on map | Day 8
Isochrone Zones | None - no action needed | Call Mapsi Isochrone API, generate 15/30-min zones, build comparison view | Split-screen: Fixed vs Isochrone | Day 9
Zone Decision | Review both options in demo, choose: Fixed or Isochrone | Present both, explain tradeoffs, recommend Fixed | Decision: Which zone type | Day 9
Booking Autocomplete | None - no action needed | Add address autocomplete (Mapsi Geocoding), dropdown suggestions | As-you-type address search | Day 10
Coverage Check | Test addresses: your home, office, random London postcodes | Implement zone validation (Turf.js point-in-polygon), show fee/status | "£50" or "£75" or "Not covered" result | Day 10
Mini-Map | None - no action needed | Add small static map showing user location + zone boundary | Visual confirmation of coverage | Day 10
Matrix API | None - no action needed | Add toggle: Haversine vs Matrix, show drive-time ranking | Accurate nearest by drive time | Day 11
Performance | None - no action needed | Add caching (localStorage), lazy loading, mobile UX improvements | Faster page loads | Day 12
Week 2 Review | Watch 5-min demo, choose zone type, test booking flow, approve/reject | Record demo video, send review with zone decision request | Zone choice confirmed | Day 13
Final Requests | Send any last-minute requests (parking info? logo change?) | Assess scope (in/out), quote if out-of-scope, implement if minor | Scope clarified | Day 14
Phase 4: Week 3 - Testing & Launch
Step | MagnetRock PetCare (Client) | Mapsi Integration Team (You) | Deliverable | Timeline
Functional Testing | None - no action needed | Test all features, cross-browser, document issues | Test report with pass/fail | Day 15
Performance Audit | None - no action needed | Run Lighthouse, fix scores <90, load testing | Scores >90 achieved | Day 16
UAT Instructions | Receive email with test checklist | Send UAT email with specific test cases | UAT email sent | Day 16
User Acceptance Testing | CRITICAL: Test on real phone, try all features, report bugs/issues by EOD | None - waiting for client feedback | Bug list from client | Day 17 (AM)
Fix UAT Issues | None - developer fixes bugs | Fix all reported bugs, retest, redeploy | All bugs resolved | Day 17 (PM)
Final Approval | Review fixes, give written approval: "Ready to launch" | None - waiting for approval | Go/No-Go decision | Day 17 (EOD)
Domain Access | Provide domain registrar login (GoDaddy, Namecheap, etc.) | None - waiting for access | Domain credentials shared | Day 18 (AM)
Vercel Transfer | Invite developer as Owner on Vercel project | Accept, configure production settings | Developer is Owner | Day 18 (AM)
DNS Configuration | None - developer handles | Point domain to Vercel, add DNS records, verify | Domain connected to Vercel | Day 18 (PM)
Soft Launch | Test live site at magnetrock.com (internal only, don't announce) | Deploy to production, monitor logs | Site live but not public | Day 18 (PM)
Soft Launch Testing | Test live production site, report any issues immediately | Monitor Vercel logs, fix hotfixes if needed | Stable production site | Day 19
Launch Approval | Give final "Go Live" approval | None - waiting for approval | Approval to announce | Day 20 (AM)
Public Announcement | Post on social media, email customers, update website nav | None - client marketing handles | Public launch! 🚀 | Day 20 (PM)
Day 1 Monitoring | Report any customer complaints or issues | Monitor live site, performance, API usage | Incident log (hopefully empty) | Day 20-21
Phase 5: Handoff & Post-Launch
Step | MagnetRock PetCare (Client) | Mapsi Integration Team (You) | Deliverable | Timeline
Admin Training | Watch 10-min training video, ask questions | Record screen capture: how to update clinic data | Training video + Q&A | Day 21
Documentation | Read UPDATE_CLINICS.md guide, bookmark for future reference | Write step-by-step guide for updating clinics, hours, fees | Admin documentation | Day 21
Mapsi Account Transfer | Create Mapsi account (mapsi.dev) with company email | Transfer API key ownership, show how to view usage/billing | Client owns Mapsi account | Day 21
Vercel Cleanup | None - already Owner | Remove developer as collaborator (optional) | Clean access control | Day 21
GitHub Cleanup | None - already has access | Remove developer as collaborator (optional) | Clean access control | Day 21
Final Payment | Pay remaining 50% (£9,000) | Send final invoice | Payment received | Day 21
7-Day Support | Report any bugs or issues via email/Slack | Fix bugs, answer questions, minor tweaks | Issues resolved | Day 22-28
Support Ends | Support period over, future work requires new quote | None - project complete | Project closed | Day 29
Ongoing Responsibilities (Post-Launch)
Task | MagnetRock PetCare (Client) | Mapsi Integration Team (You) | Frequency
Update clinic data | Edit data/clinics.json, commit, push to GitHub | None - client handles | As needed
Mapsi API billing | Pay £5-10/month Mapsi subscription | None - client pays directly | Monthly
Vercel hosting | Pay Vercel (free tier or $20/month Pro) | None - client pays directly | Monthly
Add new clinic | Add entry to clinics.json, geocode address, deploy | None (or paid support if client requests help) | Rare
Bug fixes | Report bugs to developer (if under support) | Fix bugs (if under support contract) | Rare
Feature requests | Send feature request, get quote | Quote new work, implement if approved | Occasional
API key rotation | Regenerate Mapsi API key, update Vercel env var | None (or paid support if needed) | Yearly
Monitor API usage | Check Mapsi dashboard monthly, watch for spikes | None - client monitors | Monthly
Communication Protocol
Scenario | MagnetRock Action | Mapsi Team Action | Expected Response Time
Daily progress update | Read email, reply if questions | Send email EOD with: what's done, what's next, preview link | EOD daily (Mon-Fri)
Preview URL sent | Test preview, send feedback | None - wait for feedback | Client: within 24h
Bug report | Send details: what's broken, screenshot, device/browser | Acknowledge within 2h, fix within 24h | Developer: 2h ack, 24h fix
Scope change request | Send request: "Can we add parking info?" | Respond: in-scope (free) or out-of-scope (quote price) | Developer: within 4h
UAT feedback | Send all issues found by deadline | None - wait for complete list | Client: by deadline
Launch approval | Send email: "Approved for launch" or "Wait, found issue" | Proceed with launch OR fix issue | Client: same day
Post-launch issue | Email/Slack: "Customer reported X" | Acknowledge, investigate, fix if bug | Developer: 4h ack, 24h fix
Feature request (post-launch) | Email: "We want to add Y" | Send quote, timeline, wait for approval | Developer: 48h quote
Decision Points (Client Must Decide)
Decision | When | MagnetRock Chooses | Impact
Coverage zone type | Day 9 | Fixed (postcodes) OR Isochrone (drive-time) | How coverage is calculated
Home visit fees | Day 0 | Confirm: £50 Central, £75 Inner | Displayed to customers
Closed clinic | Day 0 | Which clinic to hide (Hampstead?) | Not shown on map
Parking info | Day 14 | Add now (+£500) OR add later OR skip | Shown on clinic cards
Launch date | Day 17 | Soft launch Mon, public Wed OR delay | When site goes live
Post-launch support | Day 21 | Monthly retainer OR pay-as-you-go OR self-service | Ongoing relationship
What Client CANNOT Do (Developer Only)
Task | Why Client Can't Do It | Who Does It
Write code | Requires programming skills | Developer
Configure Vercel | Technical settings, build config | Developer
Set up Mapsi API | Technical integration | Developer
Debug errors | Requires code knowledge | Developer
Optimize performance | Requires profiling tools, code changes | Developer
Create feature branches | Git workflow knowledge | Developer
What Client CAN Do (After Training)
Task | How | When
Update clinic hours | Edit data/clinics.json, commit, push | After training (Day 21)
Add new clinic | Add JSON entry, get coordinates from Google Maps, commit | After training
Hide/show clinic | Change "status": "active" to "closed" | After training
Change fees | Edit coverage-zones.json | After training
View API usage | Login to Mapsi dashboard | Anytime
Monitor site | Check Vercel dashboard | Anytime
Summary: Who Does What
MagnetRock (Client):
✅ Provides access (Vercel, GitHub, domain)
✅ Reviews previews, gives feedback
✅ Makes decisions (zone type, fees, launch date)
✅ Tests during UAT
✅ Approves launch
✅ Pays invoices
❌ Does NOT write code
❌ Does NOT configure APIs
Mapsi Integration Team (You):
✅ Writes all code
✅ Configures Mapsi APIs
✅ Deploys to Vercel
✅ Builds features
✅ Fixes bugs
✅ Tests before client sees it
❌ Does NOT make business decisions
❌ Does NOT approve launch (client does)
Clear separation: Client decides WHAT and WHEN, Developer decides HOW.